## Overview
CPNM Replacement — API Coverage & Production Readiness
Baseline metric | Value | Planning metric | Current assessment
OpenAPI version | 3.1.0 | Resource schemas | 10
API/document version | 0.0.1 | Most likely remaining | 15–20 focused days
API paths | 18 | Optimistic | 12–14 focused days
API operations | 18 | Conservative | 22–27 focused days
Component schemas | 14 | Calendar translation | ~4–6 weeks at current working pattern
Definition of “production-ready”
The replacement is not complete merely when one-time migration scripts run.
Production-ready means the public API contract is explicitly covered or consciously redesigned.
WordPress → Salsa synchronization must be deterministic, idempotent, rerunnable, observable, and safe after partial failure.
Stable API database views form the read contract between normalized Salsa tables and the API team.
The API team should not need to reverse-engineer internal Salsa joins, locale rules, or source-specific migration semantics.
Resource serialization remains a separate layer and may be implemented in another programming language.
Daily synchronization must handle inserts, updates, deletion/unpublishing policy, replay identity, logging, exit status, and scheduling.
Deployment includes versioning/grants for API views as well as VPS/runtime, DB credentials, TLS/DNS, scheduler, monitoring, smoke tests, and rollback planning.
The frozen OpenAPI snapshot and this workbook form the bounded coverage checklist; non-OpenAPI requirements such as ConcertPodium remain in scope.
Source references
Public API docs | https://api.concertzender.nl/docs/api
Frozen project snapshot | docs/reference/concertzender-openapi-0.0.1.json
Coverage narrative | docs/api_replacement_coverage.md

## API Operations
Area | Operation | Method / path | Main response
Broadcast | broadcasts.index | GET /{locale}/broadcasts/{date} | BroadcastResource[]
Channel | channels.index | GET /{locale}/channels | ChannelResource[]
Channel | channels.show | GET /{locale}/channels/{id} | Needs real-response verification
Episode | episodes.index | GET /{locale}/episodes | EpisodeResource[]
Episode | episodes.show | GET /{locale}/episodes/{id} | EpisodeResource
Index | index | GET /{locale} | Endpoint directory
Page | pages.index | GET /{locale}/pages | PageResource[]
Playlist | playlists.index | GET /{locale}/playlists | PlaylistIndexResource[]
Playlist | playlists.show | GET /{locale}/playlists/{id} | PlaylistResource
Playlist | playlists.taxonomy.index | GET /{locale}/playlists/{taxonomyType}/index | PlaylistTaxonomyResource[]
Playlist | playlists.taxonomy.playlist.index | GET /{locale}/playlists/taxonomy/{taxonomyId} | PlaylistIndexResource[]
Post | posts.index | GET /{locale}/posts | PostIndexResource[]
Post | posts.show | GET /{locale}/posts/{id} | PostResource
Program | programs.index | GET /{locale}/programs | ProgramResource[]
Program | programs.show | GET /{locale}/programs/{id} | ProgramResource
Program | programs.episodes.index | GET /{locale}/programs/{id}/episodes | EpisodeResource[]
Search | search | GET /{locale}/search/{query} | SearchCollection
Search | search.type | GET /{locale}/search/{entryType}/{query} | SearchCollection

## Schemas
Schema / response | Kind | Domain | Referenced by ops | Current coverage
BroadcastResource | Resource | Broadcast | 1 | Partial
ChannelResource | Resource | Channel | 2 | Missing
EpisodeResource | Resource | Episode | 3 | Partial
PageResource | Resource | Page | 1 | Missing
PlaylistIndexResource | Resource | Playlist | 2 | Missing
PlaylistResource | Resource | Playlist | 1 | Missing
PlaylistTaxonomyResource | Resource | Playlist | 1 | Missing
PostIndexResource | Resource | Post | 1 | Partial
PostResource | Resource | Post | 1 | Partial
ProgramResource | Resource | Program | 3 | Audit in progress
ApiRequestStatus | Supporting schema | API wrapper | many | API-only
EntryType | Supporting schema | Search/application | 2 | Audit needed
SearchCollection | Supporting schema | Search | 2 | Missing
TaxonomyType | Supporting schema | Playlist/Search | 2+ | Audit needed
ModelNotFoundException | Reusable response | API error | 2 | API-only

## Coverage Matrix
Schema / area | Domain | Operations | Data available | Salsa storage | Migration / extraction | API database views | Resource serialization | Daily-sync readiness | Deployment relevance | Overall status | Notes
ProgramResource | Program | programs.index; programs.show; programs.episodes.index | Yes | Yes | Real WP compatibility adapter completed | Design next from completed field audit | Behavior substantially audited | Needs idempotent daily-sync wrapper | Core cutover dependency | Partial | 189 logical programs; 467 retained aliases; 365 localized program_text rows. Next handoff is stable PROGRAM view(s) plus serialization contract.
EpisodeResource | Episode | episodes.index; episodes.show; programs.episodes.index | Partial | Yes | Real WP extraction contract next | Not designed | Audit needed | Not production-ready | Core cutover dependency | In progress | Need real episode identity across translations/replays, then view grain and endpoint read contract.
BroadcastResource | Broadcast | broadcasts.index | Partial | Yes | Real WP extraction contract next | Not designed | Audit needed | Not production-ready | Core cutover dependency | In progress | Replay invariant established: replays create new broadcasts referencing original episode.
ChannelResource | Channel | channels.index; channels.show | Audit needed | No | Not implemented | Not designed | Not implemented | Not designed | Required before cutover | Missing | Theme channels are first-class API content. Source representation, storage model and read contract still need discovery.
PostResource | Post | posts.show | Partial | Yes | Partial | Not designed | Audit needed | Not production-ready | Required before cutover | Partial | Source/builders exist; full contract, view design and sync behavior still require audit.
PostIndexResource | Post | posts.index | Partial | Yes | Partial | Not designed | Audit needed | Not production-ready | Required before cutover | Partial | Likely same durable data as PostResource with a cheaper list-oriented read contract.
PageResource | Page | pages.index | Audit needed | No | Not implemented | Not designed | Not implemented | Not designed | Required before cutover | Missing | Not yet represented in replacement migration/schema work.
PlaylistResource | Playlist | playlists.show | Audit needed | No | Not implemented | Not designed | Not implemented | Not designed | Required before cutover | Missing | One of the largest remaining scope uncertainties.
PlaylistIndexResource | Playlist | playlists.index; playlists.taxonomy.playlist.index | Audit needed | No | Not implemented | Not designed | Not implemented | Not designed | Required before cutover | Missing | List contract likely shares data with PlaylistResource but should have a stable list-oriented view.
PlaylistTaxonomyResource | Playlist taxonomy | playlists.taxonomy.index | Audit needed | No | Not implemented | Not designed | Not implemented | Not designed | Required before cutover | Missing | Needs taxonomy/source discovery; current TaxonomyType vocabulary is broader than existing Salsa model.
SearchCollection | Search | search; search.type | Derived from resources | Probably no dedicated storage | No migration needed | Search read model not designed | Not implemented | Depends on stable daily-synced resources | Required before cutover | Missing | Expected to become view/query/index work after underlying resources are complete.
TaxonomyType | Taxonomy vocabulary | Playlist/Search dependency | Partial | Partial | Audit needed | Needed by resource relation views | Audit needed | Must be included in sync if durable | Potential schema/cutover blocker | Audit needed | Published vocabulary includes category, colofon, creator, default, genre, location, organization, origin, subgenre, tag.
EntryType | Application vocabulary | Search dependency | Derived | No dedicated storage needed | No migration needed | Probably no view needed | API vocabulary / serialization | API-layer only | Low | API-only / audit | Primarily response/query vocabulary; verify replacement route coverage.
ApiRequestStatus | API wrapper | Many responses | Derived | No dedicated storage needed | No migration needed | No view needed | Response-envelope work | API-layer only | Low | API-only | Response-envelope concern rather than migration data.
API index | API routing | index | Derived | No dedicated storage needed | No migration needed | No view needed | Route serialization | API-layer only | Required for compatibility if retained | API-only | Can be generated from application routes.
ConcertPodium / recordings | Non-OpenAPI domain | Not first-class in current OpenAPI | Yes/Partial | Yes | Partial | Read-contract design needed for any API exposure | Replacement-only design exists | Needs sync orchestration | Site-functionality dependency | Partial | Must remain in completeness checklist even though absent from current OpenAPI.

## Program Audit
JSON field | Actual API behavior | Salsa / source implication | API view / read contract | Serialization responsibility | Coverage | Decision / note
id | Program UUID | salsa.programs.id | Expose scalar id | Copy to JSON | Covered | Keep
type | Literal "program" | No storage needed | No view column required | Derive constant | Covered | API-only
title | Localized title; fallback to name | salsa.program_texts.title | Expose requested locale | Copy/fallback | Data path established | View owns locale selection
name | Same value as title in actual serializer | Same localized title | No separate durable value required | Emit same localized value | Behavior resolved | Do not reuse slug
slug | Localized/fallback slug in current API | salsa.programs.slug in current design | Expose scalar slug | Copy | Covered | Keep current replacement design
subtitle | Subtitle or "" | Source/storage not established | Expose nullable scalar if durable source exists | Default to "" | Audit needed | Source audit
description | Description stripped of HTML and trimmed | salsa.program_texts.description exists | Expose localized description | Strip tags/trim if compatibility retained | Partial | Extraction still incomplete
date | published_at formatted YYYY-MM-DD; else null | Publication-date source semantics need mapping | Expose source date if retained | Format date string | Audit needed | OpenAPI type/description are wrong
genre | First associated genre; General fallback | Normalized genre relation appropriate | api_program_genres-style relation view | Choose first; fallback; nest object | Partial | Do not restrict Salsa to one genre
genre.color | Hex derived from symbolic color token | Durable token may need storage/source support | Expose color token | Token → hex mapping | Audit needed | Second orange arm in legacy match is unreachable
image | Nullable; local path→route URL; external uses stored URL | Program-image relation needs mapping | Expose id/source/path/url/alt/name/caption | Build URL and fallbacks | Audit needed | No need to expose path in final JSON
mood.wave | Durable integer; default 1 | Program mood source not connected | Expose raw/nullable primitive | Default to 1 | Partial | Concept already exists
mood.intensity | Durable integer; default 1 | Program mood source not connected | Expose raw/nullable primitive | Default to 1 | Partial | Concept already exists
mood.tempo | Durable integer; default 1 | Program mood source not connected | Expose raw/nullable primitive | Default to 1 | Partial | Concept already exists
mood.svg / mood.mask | Derived URLs | No storage needed | No view columns required | Derive URLs | Covered | API-only
taxonomies | Grouped relation; items have id,name,slug | Broader taxonomy vocabulary partly covered | Separate api_program_taxonomies-style relation view | Group rows by type into arrays | Audit needed | Actual keys differ from OpenAPI
content.body | Durable rich content rendered to HTML; failure→empty string | Program content source/storage needs mapping | Expose durable content | Render/fallback | Audit needed | Serializer concern after view
content.blocks | Stored value or "" | Durable content | Expose value | Copy/default | Audit needed
content.sections | Stored value or "" | Durable content | Expose value | Copy/default | Audit needed
links.index | Route-generated | No storage needed | No view column required | Derive route | Covered
links.self | Route-generated from locale + program id | No storage needed | id + locale sufficient | Derive route | Covered
links.episodes | Route-generated from locale + program id | No storage needed | id + locale sufficient | Derive route | Covered
latest_broadcast | Replacement-only; absent from published ProgramResource | Current replacement feature | Include only if approved redesign | Serialize only if retained | Design decision | Document compatibility decision

## Workstreams
Remaining workstream | Min focused days | Max focused days | Estimate confidence | Notes
API coverage + field-level audit | 1 | 2 | High | Now in progress
Schema adjustments from audit | 0 | 2 | Medium | Overlaps with audit and implementation
Episode + Broadcast real adapter | 2 | 4 | Medium | Core radio domain; replay rule known
Media, credits, taxonomy, content completion | 1 | 2 | Medium | Horizontal completion work
Channels | 1 | 2 | Low/Medium | Source contract not yet inspected
Posts + Pages | 1 | 2 | Medium | Posts partly known; Pages new
Playlists + playlist taxonomies | 2 | 4 | Low | Largest remaining scope uncertainty
Search | 1 | 2 | Medium | Likely query/index-layer work
ConcertPodium / recording completion | 1 | 2 | Medium | Non-OpenAPI but required functionality
Production-grade daily synchronization | 2 | 4 | Medium | Idempotency, updates, deletes/unpublishing, logging, failure recovery, scheduler
API database views + index/query-plan work | 1 | 2 | Medium | Define stable read contracts per resource; document grain/locale behavior; tune underlying joins and representative view queries
API compatibility + regression testing | 2 | 3 | Medium | Include real-data regression cases
New VPS + deployment/cutover | 2 | 4 | Low/Medium | Greenhost provisioning, runtime, DB access, TLS/DNS, scheduling, monitoring, rollback
Planning view | Value
Naive minimum sum | 17
Naive maximum sum | 35
Planning range | 15–20 days (overlaps prevent simple summation)

## Read Contract
API database views — read-contract architecture
Layer | Owned concern | PROGRAM example | Must know WordPress internals? | Must know Salsa internal joins? | Notes
Normalized Salsa tables | Durable normalized domain data | salsa.programs; salsa.program_texts; genre/taxonomy relations | No | Yes | Internal data model; optimized for correctness and synchronization.
API database views | Stable query/read contract | api_programs; api_program_genres; api_program_taxonomies | No | View owner only | API team normally queries these views rather than reconstructing joins.
Resource serialization | JSON shape/defaults/derived values | ProgramResource JSON | No | No | May be implemented in PHP, Python, TypeScript, Go, etc.
HTTP API | Routing/status/pagination/response envelope | GET /{locale}/programs/{id} | No | No | Published contract boundary.
PROGRAM view proposal | Grain | Primary filter keys | Purpose | Status
api_programs | one row per salsa.programs.id + locale | id, locale | Scalar localized program fields; mood primitives; optionally image/content scalars | Proposed | Name provisional
api_program_genres | one row per program + genre + locale | program_id, locale | Localized genre relation; serializer can pick first for legacy singular genre | Proposed | Avoids row multiplication in api_programs
api_program_taxonomies | one row per program + taxonomy + locale | program_id, locale, type | Taxonomy relation rows; serializer groups by type | Proposed | Broader vocabulary still under audit
Definition of done for every production API view | Requirement
1 | Documented grain
2 | Explicit input/filter keys
3 | Deterministic locale/fallback behavior
4 | Stable column names and semantics
5 | Supporting indexes on underlying Salsa joins
6 | Representative EXPLAIN/query-plan and performance checks
7 | Regression tests using known real-data cases